## Sheet1
12
57
59
Contractor | High | Medium | Total
Contractor 1 (Mar) | 29 | 5 | 34
Contractor 2 (Mar) | 29 | 5 | 34
Contractor 3 (Now) | 30 | 5 | 35
TOTAL | 88 | 15 | 103
Person | High | Medium | Total | Problem | To Move Highs | Remains | To Move Mediums | Remarks
Desheng | 39 | 0 | 39 | ❌ Way too many highs | 36H to Contracters | 3H | +9 | 9 From Yong
Gene | 1 | 21 | 22 | ❌ Medium-heavy | 2H Add From Steve + 1H already he has | 3H | -12 | ?
Jenny | 6 | 0 | 6 | ❌ Too light | 3H (Remaining to Contracters 1 and 2, 2H already Complted by Contracter 3) | 3H | +9 | 9 From Yong
Steve | 49 | 2 | 51 | ❌ Extreme overload | 46H to Contractors | 3H | +7 | 7 From Yong
Yong | 6 | 36 | 42 | ❌ Medium-heavy | 3H to Contracters | 3H | -27 | 9 Should go to Desheng, Jenny. 7 should go to Steve
Contracter 1 | [5 empty] | 29 | +5 | +5 from Gene
Contracter 2 | [5 empty] | 29 | +5 | +5 from Yong
Contracter 3 (Abhilash) | [5 empty] | 29 | +5 | +5 from Yong

## Final Plan
BAU Developer | Existing High | Existing Medium | Existing Total | Proposed High | Proposed Medium | Proposed Total
Desheng | 39 | 0 | 39 | 3 | 9 | 12
Gene | 1 | 21 | 22 | 3 | 9 | 12
Jenny | 6 | 0 | 6 | 3 | 10 | 13
Steve | 49 | 2 | 51 | 3 | 9 | 12
Yong | 6 | 36 | 42 | 3 | 9 | 12
Contractor | Existing High | Existing Medium | Proposed High | Proposed Medium | Proposed Total
Contractor 1 (Mar) | 0 | 0 | 29 | 5 | 34
Contractor 2 (Mar) | 0 | 0 | 29 | 5 | 34
Contractor 3 (Current) | 2 | 0 | 30 | 5 | 35
TOTAL | 2 | 0 | 88 | 15 | 103
From BAU Developer | Highs Given Up | Given To Contractor(s) |  | From BAU Developer | Mediums Given Up | Given To Contractor(s)
Steve | 46 | Contractor 1, Contractor 2, Contractor 3 |  | Yong | 10 | Contractor 1 & Contractor 2
Desheng | 36 | Contractor 1, Contractor 2 |  | Gene | 5 | Contractor 3
Yong | 3 | Contractor 2 |  | TOTAL | 15 | —
Jenny | 3 | Contractor 1 & 2 (2 already completed by Contractor 3)
TOTAL | 88 | —
BAU Developer | Keeps (High) | Keeps (Medium) | Notes
Desheng | 3 | 9 | Mediums reassigned from Yong
Gene | 3 | 9 | 2 High reassigned from Steve
Jenny | 3 | 10 | 2 High already completed by Contractor 3
Steve | 3 | 9 | Majority of Highs offloaded
Yong | 3 | 9 | Largest medium donor
From BAU Developer | Highs Given Up | → Contractor 1 | → Contractor 2 | → Contractor 3 | Remarks
Steve | 46 | 15 | 16 | 15 | Majority offloaded to all 3 contractors |  | Contractor 1: 15 (Steve) + 12 (Desheng) + 2 (Jenny) = 29
Desheng | 36 | 12 | 12 | 12 | Evenly split to balance load |  | Contractor 2: 16 (Steve) + 12 (Desheng) + 3 (Yong) + 1 (Jenny) = 32
Yong | 3 | 0 | 3 | 0 | Small high spillover |  | Contractor 3: 15 (Steve) + 12 (Desheng) + 2 completed (Jenny) = 29
Jenny | 3 | 2 | 1 | 2* | *2 already completed by Contractor 3
TOTAL | 88 | 29 | 32 | 29 | Matches contractor targets
From BAU Developer | Mediums Given Up | → Contractor 1 | → Contractor 2 | → Contractor 3 | Remarks
Yong | 10 | 5 | 5 | 0 | Largest medium donor
Gene | 5 | 0 | 0 | 5 | Clean handoff
TOTAL | 15 | 5 | 5 | 5 | Perfect balance
Contractor | High Received | Medium Received | Total Programs
Contractor 1 | 29 | 5 | 34
Contractor 2 | 32 | 5 | 37
Contractor 3 | 29 (incl. 2 done) | 5 | 34
BAU Dev | Workload | Phase 1: Medium #1 (5w) | Phase 2: Medium #2–#3 (3w+3w) | Phase 3: Remaining Mediums (2w each) | Phase 4: 3 Highs (4w each) | Finish
Desheng | 9M + 3H | 12 Jan → 16 Feb | 16 Feb → 30 Mar | 30 Mar → 22 Jun (6 meds) | 22 Jun → 14 Sep | 2026-09-14
Gene | 9M + 3H | 12 Jan → 16 Feb | 16 Feb → 30 Mar | 30 Mar → 22 Jun (6 meds) | 22 Jun → 14 Sep | 2026-09-14
Steve | 9M + 3H | 12 Jan → 16 Feb | 16 Feb → 30 Mar | 30 Mar → 22 Jun (6 meds) | 22 Jun → 14 Sep | 2026-09-14
Yong | 9M + 3H | 12 Jan → 16 Feb | 16 Feb → 30 Mar | 30 Mar → 22 Jun (6 meds) | 22 Jun → 14 Sep | 2026-09-14
Jenny | 10M + 3H | 12 Jan → 16 Feb | 16 Feb → 30 Mar | 30 Mar → 06 Jul (7 meds) | 06 Jul → 28 Sep | 2026-09-28
Contractor | Start | Allocation | Ramp window | Steady execution window | Finish (planned)
Contractor 1 | 2026-03-02 | 29 High + 5 Medium | 02 Mar → 30 Mar (first highs slower) | 30 Mar → 06 Nov | 2026-11-06
Contractor 2 | 2026-03-02 | 32 High + 5 Medium | 02 Mar → 30 Mar (first highs slower) | 30 Mar → 27 Nov | 2026-11-27
Contractor 3 | 2026-01-12 | 29 High + 5 Medium (incl 2 highs already done) | 12 Jan → 09 Feb (ramp) | 09 Feb → 18 Sep | 2026-09-18
Stream | Latest finish
BAU conversions | 2026-09-28
Contractor conversions | 2026-11-27
Buffer for UAT/validation/closeout | 2026-12-01
Portfolio target | Dec 2026 met